

**Republika e Kosovës**

**Republika Kosova-Republic of Kosovo**

*Qeveria –Vlada-Government*

*Zyra e Kryeministrit-Ured Premijera-Office of the Prime Minister*

Zyra për Qeverisje të Mirë/Kancelarija za Dobro Upravljanje/Office on Good Governance

Council on the implementation of the Government Strategy for Cooperation with Civil Society 2013-2017 based on paragraph 10 (ten) of the Decision of the Government of the Republic of Kosovo No. 04/181, dated 04.02.2014, in order to ensure, coordination and monitoring the implementation of the Government Strategy for Cooperation with Civil Society 2013-2017 (hereinafter: Strategy) and the "Action Plan for implementation of the Strategy 2016 -2017" (hereinafter: Action Plan), and according to the Rules of Procedure of the Government Nr. 079/2014 dated 28.10. 2014, and duties of this Regulation.

In the meeting held on .... March 2016 approves:

**ACTION PLAN**

**Action Plan of 2016 for the implementation of the Government Strategy for Cooperation with Civil Society 2013-2017**

**Action Plan of 2016 for the implementation of the Government Strategy for Cooperation with Civil Society 2013-2017**

Based on the Rules of Procedure of the Council, the main duties defined in the Action Plan for 2016 as follows:

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Measure** | **Activity** | **Institution responsible** | **Supporting Institutions** | **Timeline of implementation** | **Financial cost and resources** | **Indocators** | **Referral documents** |
| **Regular coordination of the work of the Council** | Regular meetings of the Council | OGG, OPM, | Civikos | March, June October December |  | 4 meetings were held | Government Strategy for Cooperation with Civil Society 2013-2017 |
| **Coordination the Working Group** | Meetings of the working group - every second month | OGG/  OPM/  Working Group Coordinators | Civikos | March,  April/June, September, November |  | At least 4 meetings held from each orking group | Government Strategy for Cooperation with Civil Society 2013-2017 |
| **Monitoring the implementation of the Strategy** | Monitoring the implementation of the Strategy for all institutions which are responsible for reporting to the Council | OGG | Civikos | December2016 |  |  |  |
| **Monitoring the implementation of the Strategy**  **– Reporting of the Working Groups** | Reporting of the working groups on the work to the Secretariat and the Council - every six months- to be drafted by the secretariat and coordinators a report of all working groups | Group Coordinators/ OGG | Civikos |  |  |  |  |
| **Monitoring the implementation of the Strategy – Reports for implementation and publication** | Reporting, collection and drafting reports by the Secretariat, their approval in the Council and publication of reports | Group Coordinators/ OGG | Civikos |  |  |  |  |
| **Review of the Strategy and Action Plan** | Following the recommendations of the evaluation and the review of the strategy | OGG/OPM and the Council | Civikos |  |  |  |  |

***Attention: \* Council and the responsible institutions will publish reports in Braille and sign language***

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Action** | **Institions responsible** | | **Supporting Institutions** | **Success indicators** | **Timeline of Implementation** | **Achievment rates (A, B, C, D or E)** | | **Comments** | **Financial cost and resources** | |
| **Priorities for implementation of the Strategy for 2016**  **Strategic Objective: 1. Ensured and strengthening participation of civil society in drafting and implementation of policies and legislation** | | | | | | | | | | |
| **Measure/Strategic sub-objective: 1.1. Draft / Amendment of basic legislation / reference to CSO involvement in drafting and implementation of policy** | | | | | | | | | | |
| **Measure indicator: 1.1. Basic legislation on CSO involvement in drafting and implementation of policy is drafted** | | | | | | | | | | |
| **1.1.1. Identification of relevant legislation indicating the involvement of CSOs in drafting and implementation of policy** | **OPM (Legal Office)** | | **Line Ministries, CSOs; othe competent instituions** | **1.1.1. Legislation that affects the involvement of CSOs in drafting and implementation of policy is identified** | **June 2016** | |  |  | **5.000 EUR** |
| 1.1.1.a  Analysis and review of legislation regarding the participation of CSOs in drafting and implementation of policies and legislation | OPM (Legal Office) | | Line Ministries; CSOs; | Legal analysis regarding the CSOs involvement in draftingand implementation of policies and legislation was consulted and published | June 2016 | |  |  |  |
| **1.1.2. Addressing of identified issues based on the recommendations of analysis** | **Line Ministries, Other competent institutions** | | **OPM (Legal Office), CSOs:** | **1.1.2. Secondary legislation for implement of the legislation in force are drafted** | **July - Decmebr 2016** | |  | **Following the publication of the analysis, the cost activities to be analysed in detail** | **1.000 EUR** |
| **Measure/ Strategic sub-objective: 1.2. Determination the standards of CSO involvement in drafting and implementation of policies and legislation** | | | | | | | | | | |
| **Measure indicator: 1.2. Setting of minimum standards on CSOs involvement** | | | | | | | | | | |
| **1.2.1. The establishment of the platform / database which provides information on the profile of civil society organizations on the basis of their fields of action** | **OPM (Office on Good Governance)** | | **OPM (Legal Office, Office on Strategic Planning, Administrative Office, Coordinating Secretariat of the Government); MPA (DOJQ); CSOs;** | **1.2.1Information on the profile of civil society organizations through research based on their fields of action provided** | **August 2016** | **Upon the approval of the regulation on minimum standards the activity shall change** | |  | **5,000 EUR** |
| 1.2.1a. Design of the online platform | OPM (Office on Good Governance) | | Office of Strategic Planing, Administrative Office, Coorinating Secretariat of the Government); MPA (DRNOJQ); CSOs; | 1.2.1.a The online platform is programmed and ready for use | June 2016 |  | |  |  |
| 1.2.1.b Testing and operationalization of the platform | OPM (Office on Good Governance) | | Office of Strategic Planing, Administrative Office, Coorinating Secretariat of the Government); MPA (DRNOJQ); CSOs; | 1.2.1.b The online platform is tested and open for the public | August 2016 |  | |  |  |
| **1.2.2.**  **Approval of the Regulation on minimum standards for public consultation** | **OPM (Legal Office)** | |  | **1.2.3. Regulatory act on minimum standards for CSOs involvement in drafting of policies and legislation is approved** | **March 2016** |  | |  | **Administrative cost** |
| **1.2.3. Promovimi i rregullores për standardet minimale të përfshirjes së OShC në hartimin e politikave dhe legjislacionit.** | **LO/OPM in cooperation with (Communication Office);** | **OPM (Legal Office; Office on Good Governance); CSOs** | | **1.2.4. Promotion of the Regulation on minimum standards of CSO involvement in drafting of policy and legislation.** | **April – August 2016** |  | |  | **5,000 EUR** |
| **Measure/Strategic sub-objective: 1.3. Professional capacity building of civil servants and members of civil society organizations in drafting and implementation of policies and legislation** | | | | | | | | | | |
| **Measure indicator: 1.3. Professional capacity building of civil servants and members of CSOs** | | | | | | | | | | |
| **1.3.1. Identification of the responsible officials who are envolved in drafting of policy and legislation, to be included in training for the regulation of minimum standards for public consultation** | **OPM (Office on good Governance and Legal Office);** | | **OPM (Legal Office, Office on Strategic Planing); MPA (Administration department of Civil Servant; IKAP); CSOs;** | **1.3.1.a The list of officials responsible for involvement in trainings for implementing of the Regulation** | **April 2016** |  | |  |  |
| **1.3.2. Drafting programs for continuous training of civil servants and CSO** | **OPM - Office on Good Governance, Legal Office and CSOs** | | **OPM (Legal Office, Office on Strategic Planing); MPA (Department of Civil Servant Administration; IKAP); CSOs;** | **1.3.2. Programs for continues training of civil servants and CSOs are drafted** | **April -May 2016** |  | |  | **10,000 EUR**  **and donors** |
| 1.3.2.a Drafting of training module on minimum standards for the Group of Trainers for the legislative drafting process | OPM (Office on Good Governance in cooperation with Legal Office); IKAP; dhe OSHC-të | |  | 1.3.2.a The training modules are submitted and approved to KIPA | April - May 2016 |  | |  |  |
| 1.3.2.b  Drafting of training module for minimum standards for the responsible officials who are envolved in drafting of policy and legislation, and representatives of CSOs | OPM (Office on Good Governance and legal Office); IKAP; CSOs | |  | 3.2.b Traning modules submitted to IKAP and approved | April - May 2016 |  | |  |  |
| **1.3.3. Organized traings for civil servants and CSOs representatives** | **MPA (IKAP); CSOs** | | **OPM (Legal Office, Office on Strategic Planing; Office on Good Governance); MPA (Department of Civil Servant Administratio, CSOs;** | **1.3.3. Organized traings for civil servants and CSOs representatives** | **June -Decmebr 2016** |  | |  | **40,000 EUR**  **the cost for three days training with 800 participants to be confirmed.** |
| 1.3.3.a Organization of trainings by KIPA to identify all responsible officials and representatives of the interested CSOs | MPA (IKAP); CSOs | | OPM (Legal Office, Office on Strategic Planing; Office on Good Governance); MPA (Department of Civil Servant Administration); CSOs; | 1.3.3.a. Trainings for all officials responsible identified and interested representatives of CSOs were held | June - Decmber 2016 |  | |  |  |
| 1.3.3.b Training on minimum standards envolved in the list / catalog of mandatory training of KIPA | MPA (IKAP) | |  | 1.3.3.b. Trainig on minimum standard is an obligatory part of the list / catalog training of KIPA | October 2016 |  | |  |  |
| **Measure/Strategic sub-objective: 1.4. Building of the monitoring and reporting system on CSO involvement** | | | | | | | | | | |
| **Measure indicator: 1.4. Building of monitoring and reporting system** | | | | | | | | | | |
| **1.4.1.**  **Creating a monitoring mechanism for the implementation of standards for public consultation** | **OPM (Office on Good Governance)** | | **OPM (Legal Office, Office of Strategic Planing, Coordinating Secretariat of the Government, Public Communication Office); CSOs** | **1.4.1. A mechanism for monitoring the implementation of standards for public consultation established** | **October - Decmber 2015** |  | | **Human resources** | **20,000 EUR** |
| 1.4.1.a  Identification and adaptation / drafting of implementation mechanisms to ensure reporting and monitoring of the Regulation on Standard Minimum | OPM (Office on Good Governance, LO, OSP, CSG, PCO) | |  | 1.4.1.a.  All of the implementation mechanisms for reporting and monitoring of the Standard Minimum Standards adapted and ready for implementation | April - July 2016 |  | |  |  |
| **1.4.2 Continued of monitoring and reporting of the involvement of CSOs** | **Instituion/s responsible for implementation of certain plan** | |  | **1.4.4. Implementation of the Standard Minimum Rules monitored and reported on a regular basis** | **September - Decmber 2016** |  | |  | **Administrative cost** |
| 1.4.2.a Continued monitoring of the implementation of the Regulation on Minimum Standards | Instiution/a responsible for monitoring of Minimum Standards | |  | 1.4.2.a Implementation of the Regulation on Minimum Standards continuously monitored | September - December 2016 |  | |  |  |
| 1.4.2.b. Reporting regularly on implementation of the Regulation on Minimum Standards | Instiution/a responsible for monitoring of Minimum Standards  e | |  | 1.4.2.b Implementation of the Regulation on Minimum Standards to be reported on regular basis | September - December 2016 |  | |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Action** | **Institions responsible** | **Supporting Institutions** | **Success indicators** | **Timeline of Implementation** | **Achievment rates (A, B, C, D or E)** | **Comments** | **Financial cost and resources** |
|  |  |  |  |  |  |  |  |
| **Strategic Objective: 2.**  **Building system of contracting public services for civil society organizations** | | | | | | | |
| **Measure/Strategic \_sub-objective: 2.1.**  **Drafting of the legal framework that regulates the procedures of contracting public services by CSO, and which defines the areas of contracting** | | | | | | | |
| **Measure indicator: 2.1. Legal framework for regulating the procedures of contracting public services by CSOs is drafted** | | | | | | | |
| **2.1.1.**  **Ongoing work of a joint group on building system for contracting public services by CSO according to the mandate** | **OPM (Office on Good Governance); Establishment of a joint group** | **KRPP, Ministry of Finance, Line Ministries, Other competent institutions; CSOs** | **2.2.1. Number of meetings and job performance by joint bodies for setting the standards and principles for contracting public services by CSO according to action** | **Ongoing** | **Evaluation not at the high level** |  | **300 euro** |
| **2.1.2. Identification and analysis of the current legal framework for regulating the procedures of contracting public services by CSO** | **OPM (Legal Office); Establishment of a joint group** | **Line Ministries, Other competent instituions; CSOs** | **2.1.1. The actual legal analysis for regulation of contracting public services procedures by CSO is consulted and published** | **April - June 2016** |  |  | **5000 EUR** |
| 2.1.2.a The report with recommendations to amend and supplement the current legislation for regulating the procedures of public services by CSO | OPM (Legal Office); Establishment of a joint group |  | a) The report with recommendations drafted and published  b) The number of recommendations that were taken into account by the published report | September 2016 | LO |  | Without cost |
| **2.1.3. Identification of the areas that CSOs can be contracted to provide public services** | **MLSW Establishmment of a joint group** | **OPM (OGG, Office of Strategic Planing); Line Ministries, Other competent instituions; CSOs** | **2.1.3. Identified areas in which CSOs can be contracted to provide public services** | **March - September 2016** |  |  | **7,000 EUR** |
| 2.1.3.a  Research of certain areas that currently contracted for the provision of public services by CSO | MLSW- Establishment of a joint group |  | List of NGOs that are contracted by ministries to provide public services | March - September 2016 |  |  |  |
| 2.1.3.b Research and identification of new areas of contracting public services by CSO | OPM (Office on Good Governance); Establishment of a joint group |  | Civil society sector are consulted and new areas for contacting public services identified | September 2016 |  |  |  |
| **2.1.4. Research of the type of services that currently provided by CSOs** | **MLSW/ Establishment of a joint group** | **OPM (Office on Good Governance, Line Ministries, Other competent instituions; CSOs** | **2.1.3.** **Research on the types of services currently provided by the CSO is made** | **March - September 2016** |  |  | **5.000 EUR** |
| 2.1.4.a. Identification of the type of services that currently provided by CSO | MLSW/ Establishment of a joint group | OPM (Office on Good Governance); | Provision of services Identified and published | **September 2016** |  |  |  |
| **2.1.5. The list of public services that can be contracted by CSO** | **MPMS/ Grupi i përbashkët i themeluar** | **ZKM (Zyra për Qeverisje të Mirë); Ministritë e linjës, Institucionet tjera kompetente; OSHC-të** | **2.1.6. Janë kataloguar shërbimet publike që mund të kontraktohen nga OSHC** | **December 2016** |  |  | **15,000 EUR** |
| 2.1.5.a. Drafting of Catalog of the public services that can be contracted by CSO | MLSW | OPM (Office on Good Governance); |  | **December 2016** |  |  |  |
| 2.1.5.b. Publication of the catalog | MPMS dhe OPM (Office on Good Governance); |  |  | **December 2016** |  |  |  |

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Action** | **Institions responsible** | **Supporting Institutions** | | **Success indicators** | **Timeline of Implementation** | **Achievment rates (A, B, C, D or E)** | **Comments** | **Financial cost and resources** |
|  |  |  | |  |  |  |  |  |
| **Strategic Objective: 3. Building system and defined criteria for financial support for CSOs** | | | | | | | | |
| **Measure/Strategic sub-objective: 3.1. Reform of legislation for implementation of joint projects** | | | | | | | | |
| **Measure indicator: 3.1. Legislation for financing of projects implemented by CSOs are drafted and adapted** | | | | | | | | |
| **3.1.1. Analysis of existing legislation for the implementation of joint projects** | **Ministry of Finance** | **KRPP; OPM (Legal Office); CSOs** | | **3.1.1. The existing legislation for the implementation of common policies and projects is analysed** | **March - June 2016** |  | **Joint implementation of projects implies contraction of CSOs to implement parts / certain projects of the government program** | **5,000 EUR** |
| **3.1.2. Adapting the legislation according to needs identified through analysis** | **Ministry of finance** | **KRPP; OPM (Legal Office); Line Ministries; CSOs** | | **3.1.2. The legislation according to the needs identified through analysis is adapted** | **June - Decmber 2016** |  |  | **10,000 EUR** |
| **Measure/Strategic sub-objective: 3.2. Creating the environment for philanthropy and sponsorship** | | | | | | | | |
| **Measure indicator: 3.2. Appropriate environment for philanthropy and sponsorship cre** | | | | | | | | |
| **3.2.1. Drafting and approval of the concept paper on philanthropy and sponsorship** | **OPM (LO)** | **Line Ministries; CSOs,**  **Ministry of Finance** | | **3.2.1. The Concept Paper on philanthropy and sponsorship is drafted and approved** | **March-December 2016** |  | **The general concept paper, not limited to any particular sector** | **15,000 EUR** |
| 3.2.1.a Drafting a concept paper, including a public consultation with all parties of interest | OPM (LO) | Ministry of Finance; Line Ministries; CSOs | |  | March - October 2016 |  |  |  |
| 3.2.1.b Approval of the concept-document | OPM (LO) | Ministry of Finance; Line Ministries; CSOs | |  | December 2016 |  |  |  |
| 3.2.1.c Implementation of the recommendations arising from the concept paper | Instituions responsible |  | |  | 2017 |  |  |  |
| **Measure/Strategic sub-objective: 3.3. Standardization of public benefit status** | | | | | | | | |
| **Measure indicator: 3.3.**  **The public benefit status is adapted and standardized** | | | | | | | | |
| **3.3.1. Harmonization of legislation and mechanisms of public benefit status** | **MPA (DOJQ)** | | **OGG, Ministry of Finance, CSOs; OPM, (Legal Office)** | **3.3.1. Legislation and mechanisms of public benefit status is harmonized** | **January - December 2016** |  |  | **2000 EUR** |
| 3.3.1.a. Drafting and approval of the concept paper for the freedom of association of NGOs, which deals with the financial status of Public Benefit | MPA (DOJQ) | | OGG, Ministry of Finance, CSOs; OPM, (Legal Office) |  | May 2016 |  |  |  |
| 3.3.1.b Implementation of the recommendations arising from the concept paper | Instituions responsible | |  |  | December 2016 |  |  | 2.000 EUR |
| **Measure/Strategic sub-objective: 3.4. Involvement of civil society in mechanisms for coordination with donors** | | | | | | | | |
| **Measure indicator: 3.4. Civil Society is involved in mechanisms for coordination with donors** | | | | | | | | |
| **3.4.1.**  **The opening of the existing mechanism and database of donor contributions and for the use by CSOs** | **Ministry of European Integration** | **OPM (Office on Good Governance); CSOs** | | **3.4.1. Database of donors for input and use from CSOs opened** | **January - August 2016** |  |  | **Administrative Cost** |
| 3.4.1.a  Organizing training for use of the Donor Database for civil society organizations, accordingly | Ministry of European Integration | OPM (Office on Good Governance); CSOs | |  | Ongoing during 2016 |  |  |  |
| 3.4.1.b Decision or Amendment and supplementation of the Regulation on Coordination with Donors to include civil society in the High Donors Forum and its sub-working groups | OPM, Ministry of European Integration |  | |  | June 2016 |  |  |  |
| 3.4.1.c  Selection of members by civil society, according to open, democratic and transparent procedures | Ministry of European Integration | CiviKos, Council | |  | August 2016 |  |  |  |
| **Measure/Strategic sub-objective: 3.5. Determination of criteria for granting and implementation of grants from public funds** | | | | | | | | |
| **Measure indicator: 3.5. Grants from public funds are distributed and implemented based on predefined criteria** | | | | | | | | |
| **3.5.1. Përcaktimi dhe zbatimi i modelit per perkrahje financiare te shoqerise civile nga fondet publike** | **OPM (Office on Good Governance)** | **Ministry of Finance; CSOs** | | **3.5.1. Është përcaktuar modeli i perkrahjes financiare te shoqerise civile nga fondet publike** | **March - December 2016** |  |  | **17,000 EUR**  **TA EU** |
| 3.5.1.a Recommendation of the Council and the government decision on the financial support model of civil society by public funds | Council for the implementation of the Strategy, the Government |  | |  | April 2016 |  |  |  |
| 3.5.1.b Drafting and adoption of the act / normative acts for the implementation of the model set | MF | OPM (OGG, LO); CSOs | |  | August 2016 |  |  | 5000 EUR |
| 3.5.1.c. Promotion of adopted act / normative acts | MF, OPM (OGG) | CSO | |  | September - December 2016 |  |  | 2000 EUR |
| 3.5.1.d Capacity building for implementation of the adopted act / normative acts | MF, OPM (OGG), IKAP |  | |  | September - December 2016 |  |  | 10,000 EUR |
| **3.5.2.**  **Publication of reports on eligible projects, beneficiary CSOs and the results of projects** | **OPM** | **OPM (Office on Good Governance); Ministry of Finance; CSOs** | | **3.5.7. Janë publikuar raportet mbi projektet përfituese, OSHC-të përfituese, dhe rezultatet e projekteve** | **March - June 2015** |  |  |  |
| 3.5.2.a  The decision for proactive publication of all funds that are separate from the Kosovo budget for NGOs during 2015 and 2016 | OPM | MF | |  | March 2016 |  |  |  |
| 3.5.2.b Development and application of the format / unique form for publishing information | OPM, Ministry of Finance | Council | |  | April 2016 |  |  |  |
| 3.5.2.c Publication of all government units for 2015 | OPM, Line Ministries | Ministry of Finance | |  | June 2016 |  |  |  |
| 3.5.2.d Publication of all government units for 2016 | OPM, Line Ministries | Ministry of Finance | |  | February 2017 |  | **February 2017** |  |
| **3.5.3. Support of projects / co- financing of CSOs with a certain percentage of EU funding for civil society** | **Ministry of European Integration** | **Ministry of Finance; CSOs** | | **3.5.3. Janë përkrahur projektet e OSHC me përqindje të caktuar** | **2017** |  |  |  |
| 3.5.3.a The decision on the establishment of the scheme for automatic co-financing of CSO projects financed by the EU (as determined by the percentage of the EU) | Ministria e Integrimit Evropian | Ministry of Finance | |  | June 2016 |  |  |  |
| 3.5.3.b  Involvement of the relevant funds in the budget of Kosovo for 2017 and MTEF | Ministry of Finance | MEI | |  | December 2016 |  |  |  |
| **Measure/Strategic sub-objective: 3.6.**  **Setting criteria for non-financial support for CSOs** | | | | | | | | |
| **Measure indicator: 3.6. Criteria for financial support for CSOs are not defined** | | | | | | | | |
| **3.6.1.**  **Analysis of current legislation that regulates the non-financial support** | **OPM (Legal Office)** | **Line Ministries; CSOs** | | **3.6.1. Është analizuar legjislacioni i tanishëm që rregullon mënyrën e përkrahjes jo financiare** | **March - December 2016** |  |  | **10,000 EUR**  **+ ensurance by donors** |
| 3.6.1.a  Engaging an expert in the field for the analysis of the legislation in force | OPM |  | |  | March - December 2016 |  |  |  |
| 3.6.1.b Discussion and validation of recommendations with all parties of interest | OPM |  | |  | March - December 2016 |  |  |  |
| 3.6.1.c  Inclusion in the 2017 legislative agenda of the laws that are recommended to be drafted / amended | OPM |  | |  | December 2016 |  |  |  |

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Action** | **Institions responsible** | | **Supporting Institutions** | **Success indicators** | **Timeline of Implementation** | **Achievment rates (A, B, C, D or E)** | **Comments** | **Financial cost and resources** |
|  |  | |  |  |  |  |  |  |
| **Strategic Objective: 4.**  **Promoting an integrated approach to the development of volunteering** | | | | | | | | |
| **Measure/Strategic sub-objective: 4.1. Identifying the needs and profile of volunteering in Kosovo** | | | | | | | | |
| **Measure indicator: 4.1. Needs and profile of volunteering in Kosovo have been identified** | | | | | | | | |
| **4.1.1. Functioning of volunteering intersectoral group (regular group meetings)** | | **OGG** | **All actors responsible including CSOs** | **4.1.2. Functioning of inter-sectoral group on volunteering. Regular meetings of the griup were held** | **March 2016- First meeting  June 2016-Second meeting  November2016- Third meeting** |  |  | **Administrative cost** |
| 4.1.1.a. – Development of work plan of the group | | OGG |  | 4.1.2.a The work plan is drafted | June 2016 |  | Regular communication and cooperation with the Council |  |
| **4.2.1. Analysing of the volunteering profile in Kosovo** | | **Established group** |  | **4.1.3. The volunteering profile in Kosovo analysed** | **March - October 2016** |  |  |  |
| **4.2.2. Preparation of terms of reference for the analysis of the volunteering profile in Kosovo** | | **OGG 1st group established** |  | **4.1.3.1**  **Terms of reference for the four tests of the unit prepared** | **April - May 2016** |  |  |  |
| 4.2.2.a Analysis of legislation affecting volunteerism | | OGG/Working Group | OGG/MF, Council, donors, CSO | Detailed analysis, consulted and published | June –October 2016 |  |  | 10,000 EUR |
| 4.2.2.b Analysis of the civil society sector (examples of success and lessons learned) | | OGG/Working Group | OGG/MF, Council, donors, CSO | Detailed analysis, consulted and published | June –October 2016 |  |  | 10,000 EUR |
| 4.2.2.c Analysis of international experience (case studies) | | OGG/Working Group | OGG/MF, Council, donors, CSO | Detailed analysis, consulted and published | June –October 2016 |  | 10,000 Eur for reserach 10,000 Eur for study visit | 20,000 EUR |
| 4.2.2.d Analysis of volunteeries motivation in Kosovo | | OGG/Working Group | OGG/MF, Council, donors, CSO, Universities | Detailed analysis, consulted and published | June –October 2016 |  |  | 10,000 EUR |
| 4.2.2. e Conference for the publication of analyses and recommendations | | OGG | OGG/MF, Council, donors, CSO | Conference held | June –October 2016 |  |  |  |
| 4.2.2.f Drafting of general recommendations by the working group. | | OGG/Working Group | OGG/MF, Council, donors, CSO | Conference held | June – October 2016 |  |  | 3,000 EUR |
| 4.2.2.g  Introducing in the government agenda the recommendations arised by the analysis | | OGG/Working Group | OGG/MF, Council, donors, CSO | Conference held | December 2016 |  |  |  |
|  | |  |  | Application for membership by OGG | June 2016 |  |  |  |
| 4.3. The membership of the Republic of Kosovo in regional and international volunteering mechanisms. | | OGG/  OPM |  |  |  |  |  |  |